## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Status
Home page | Public | Medium | Iteration 1 | HE150464 | Bùi Minh Trang | Done
User Login | Public | Medium | Iteration 1 | HE153693 | Vũ Hoàng Phúc | Done
User Register | Public | Medium | Iteration 1 | HE153693 | Vũ Hoàng Phúc | Done
Reset password | Common | Complex | Iteration 2 | HE153693, HE153633 | Vũ Hoàng Phúc(BE-FE-80), Nguyễn Quang Hiếu (Mail-20) | Done
Change password | Common | Medium | Iteration 1 | HE153693 | Vũ Hoàng Phúc | Done
User Authorization | Common | Complex | Iteration 1 | HE153633 | Nguyễn Quang Hiếu | Done
View medical examnination | Customer | Medium | Iteration 3 | HE153633 | Nguyễn Quang Hiếu | Done
Setup medical examnination | Doctor | Complex | Iteration 3 | HE153613, HE153633 | Nguyễn Minh Hùng(BE-50), Nguyễn Quang Hiếu(FE-50) | Done
Control medical examnination | Admin | Complex | Iteration 3 | HE153613, HE153633 | Nguyễn Minh Hùng(FE-50), Nguyễn Quang Hiếu(BE-50) | Done
Patient List | Doctor | Simple | Iteration 2 | HE153789 | Nguyễn Minh Hoàng | Done
Doctor List | Admin | Simple | Iteration 2 | HE153789 | Nguyễn Minh Hoàng | Done
Patient feedback | Customer | Medium | Iteration 2 | HE153789 | Nguyễn Minh Hoàng | Done
View feedback list | Doctor | Simple | Iteration 2 | HE153789 | Nguyễn Minh Hoàng | Done
Feedback detail | Doctor | Medium | Iteration 2 | HE153789 | Nguyễn Minh Hoàng | Done
Reservation List | Doctor | Simple | Iteration 2 | HE153613 | Nguyễn Minh Hùng | Done
Reservations | Customer | Complex | Iteration 2 | HE153613 | Nguyễn Minh Hùng | Done
Reservation details | Customer | Simple | Iteration 2 | HE153613 | Nguyễn Minh Hùng | Done
News list | Public | Medium | Iteration 1 | HE153789 | Nguyễn Minh Hoàng | Done
News details | Public | Medium | Iteration 1 | HE153789 | Nguyễn Minh Hoàng | Done
Sliders | Public | Complex | Iteration 1 | HE153789 | Nguyễn Minh Hoàng | Done
Introduction | Public | Simple | Iteration 1 | HE150464 | Bùi Minh Trang | Done
Services list | Public | Simple | Iteration 1 | HE150464 | Bùi Minh Trang | Done
Services details | Public | Medium | Iteration 1 | HE150464 | Bùi Minh Trang | Done
Admin dashboard | Doctor | Complex | Iteration 2 | HE153633, HE153613 | Nguyễn Quang Hiếu(FE-50), Nguyễn Minh Hùng(BE-50) | Done
Setting list | Doctor | Simple | Iteration 3 | HE153633 | Nguyễn Quang Hiếu | Done
Setting details | Doctor | Medium | Iteration 3 | HE153633 | Nguyễn Quang Hiếu | Done
User profile | Common | Medium | Iteration 2 | HE153693 | Vũ Hoàng Phúc | Done
Update user profile | Common | Medium | Iteration 2 | HE153693 | Vũ Hoàng Phúc | Done
Jobs application | Public | Medium | Iteration 3 | HE153633 | Nguyễn Quang Hiếu | Done
Laboratory results | Common | Complex | Iteration 3 | HE150464 | Bùi Minh Trang | Done
Automatically clear the reservation | System | Complex | Iteration 3 | HE153633, HE153613 | Nguyễn Quang Hiếu-50, Nguyễn Minh Hùng-50 (Only BE) | Done